## Slide 1
Channel Attribution & Prediction — Committed Timeline
AI2 · TD Marketing
DONE TO DATE
✓ XGBoost + DR model built (uplift + attribution code)
✓ Measurement-team AZ access secured
✓ GPU + experiment infra in place
✓ Transformer research done — build underway
Sep '26
Nov
Jan '27
Mar
May
Jul
Sep
Nov
CHANNEL PREDICTION
Next-best-journey · client: CLIP campaign
Built on our end (GPU) · MDR required
CHANNEL ATTRIBUTION
MTA / MMM · client: measurement team
V1–V2 on their AZ (no prod approval)
V3 on our end (GPU) → validation
MDR / Model Validation · Dec–Feb
Model Validation · Jul–Sep
✓
✓ Delivered Aug '26
P·V1 — XGB + DR uplift
baseline; codebase reused for attribution V1
Nov 30, 2026 (target Oct 31)
P·V2 — Transformer next-best-journey
no XGB V2 — we jump straight to the transformer; holds team priority through Oct
Mar 2027
Production
campaign uses it from Apr 2027
Sep 30, 2026
A·V1 — Fractional attribution (their AZ)
XGB + DR code exists (~2 wk); used directly — no approval delay
A·V2 — MMM-informed attribution (XGB + DR, their AZ)
starts Nov, once the transformer enters MDR · needs MMM ROI extracts + incrementality results
SIMPLE
Calibration Jan 29, 2027
BAYESIAN
Priors Mar 31, 2027
Jun 30, 2027
A·V3 — Transformer attribution, on our end
needs GPU (their AZ has none); reuses the predictive data pipeline + infra
Target Q4 2027
Deployment
after Model Validation (Jul–Sep)
Committed dates include buffer · 2 FTEs across both streams — the prediction transformer holds priority through Oct 2026, then attribution takes the freed capacity while the MDR runs · Attribution V1–V2 run as analytics on the measurement team's AZ, so no production-model approval is needed; V3 is trained on our end and follows the validation path, which is why it reaches them later · External inputs: MMM ROI extracts, incrementality test results

## Slide 2
Basis of Estimates — Where Built, Who Uses It, What's Reused
Milestone | Built where | Effort | Committed date | Who uses it · notes & reuse
P·V1 — uplift model (done) | Our AZ | 2 wk | Delivered Aug 2026 | Team-internal baseline (XGB + DR, uplift training). Codebase is reused for attribution V1.
P·V2 — transformer next-best-journey | Our end (GPU) | ~8 wk | Nov 30, 2026 (target Oct 31) | CLIP campaign, after approval. No XGB V2 — we jump straight to the transformer; it holds team priority through Oct.
P — production | MDR → prod | Dec–Feb | Mar 2027 · campaign use Apr | MDR opens once the model is finalized; extension possible with justification.
A·V1 — fractional attribution | Measurement team's AZ | 2 wk | Sep 30, 2026 | Measurement team, directly. Runs as analytics on their AZ (access in hand) — no production-model approval, no deployment delay. Building on our end instead would require the full data pipeline + validation (≈ +8–10 wk).
A·V2 — MMM-informed attribution | Measurement team's AZ (XGB + DR) | 4–6 wk | Simple: Jan 29, 2027 Bayesian: Mar 31, 2027 | Measurement team. Starts Nov, once the transformer is in MDR. Needs MMM ROI extracts + incrementality test results. Calibration logic later reusable as priors/regularizer for the transformer.
A·V3 — transformer attribution | Our end (GPU — their AZ has none) | ~8 wk | Model: Jun 30, 2027 | Reuses the predictive model's data pipeline + GPU infra, so it is a build, not a research project. Add ~8 wk if the MMM must be built in-house first.
A — deployment | Model Validation → prod | Jul–Sep | Target Q4 2027 | Measurement team + downstream reporting. Lands later because prediction is prioritized and V3 must pass validation (new architecture ⇒ new approval path).
Sequencing rationale. Anything built on our end must pass Model Validation before a partner can use it, so attribution V1–V2 are deliberately built on the measurement team's AZ for immediate use, and the approval path is reserved for the transformer versions. The prediction transformer holds priority through October; attribution work interleaves (V1) and then absorbs the freed capacity while the MDR runs. Dates are commitments with buffer, not best-case estimates.